## Sheet1
Story | Estimate | Priority | Sprint Added | Sprint Completed
As a user, I can open the UI for the graphic rendering program so I can view or create projects | 20 | 1 | 1 | 2
As a user I want to access data to render a single shape or text object | 7 | 2 | 2 | 2
As a user, I can draw shapes and text so that I can make pictures. | 20 | 3 | 1 | 1
As an admin, I want to delete rendered objects. | 2 | 4 | 2 | 2
As an admin, I can save art projects and open them between execution of the program. | 4 | 5 | 2 | 2
As an admin, I want to move existing shapes and text. | 10 | 6 | 2 | 2
As an admin, I want to be able to copy a rendered object | 20 | 7 |  | 2
As an admin, I want to select drawing settings for shapes I want to draw. | 5 | 8 |  | 2
As a user I want to be able to add word art to my text | 8 | 9 |  | 2
As an admin, I want to be able to change the size of the graphics rendering window | 4 | 10 |  | 2
As a guest, I want to contact the developers of the program for feedback. | 4 | 11 | 2 | 2