## Sheet1
Task | Product Backlog Item | Volunteer | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Sprint Review
1 | User Stories | All Members | Complete | 2 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0
2 | Planning for 1st Print | All Members | Complete | 2 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
3 | Investigated Qt | All Members | Complete | 6 | 0 | 1 | 2 | 2 | 0 | 0 | 2 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Total: | 0 | 1 | 2 | 2 | 1 | 6 | 2 | 0
Task | Product Backlog Item | Volunteer | Status | Original Estimate | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Sprint Review
6 | Initial Setup (Git) | Aaron | Complete | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
7 | Investigated QtPainter | All Members | Complete | 6 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0
8 | Planning for 2nd Sprint | Aaron | Complete | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0
9 | Familiarize with Git | All Members | Complete | 6 | 0 | 0 | 0 | 0 | 2 | 3.5 | 2 | 0
|  |  |  | Total: | 3 | 3 | 1 | 2 | 2 | 3.5 | 2 | 0