## Sheet1
Task | Product Backlog Item | Volunteer | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Sprint Review
1 | Shapes | Aaron | Complete | 20 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0
2 | Vector | Garrett | Complete | 5 to 7 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 0
3 | Product Backlog | Zayn | Complete | 3 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
4 | Sprint Backlog | Chance | Complete | 4 | 0 | 1 | 1.5 | 0 | 1 | 0 | 0 | 0
5 | User Interface | Misha | Complete | 20 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0
6 | Shapes Parser | Stephen & Aaron | Complete | 20 | 0 | 0 | 0 | 0 | 0 | 4 | 7 | 0
|  |  |  | Total: | 4 | 5 | 3.5 | 1 | 5 | 4 | 7 | 0
Task | Product Backlog Item | Volunteer | Status | Original Estimate | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Sprint Review
6 | User Interface | Misha & Aaron | Complete | 20 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0
7 | Sprint Backlog | Chance | Complete | 4 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
8 | Deoxygen | Garrett | Complete | 7 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0
9 | Shapes Parser | Stephen & Aaron | Complete | 20 | 13 | 6 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Total: | 13 | 13 | 0 | 0 | 0 | 0 | 0 | 0